

ECB-UNRESTRICTED

Pre-Migration Schedule  
for T2 Participants

T2-T2S Consolidation 14.12.2022

Version 1.1 Final

**Version Control**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Version** | **Date** | **Author** | **Distribution** | **Explanation** |
| **0.1** | 3-06-2022 | ECB | MTRSG | Initial draft version shared with Central Banks |
| **0.2** | 10.06.2022 | ECB | TCCG | Second version shared with members of the TCCG. |
| **0.3** | 29.08.2022 | ECB | MTRSG | Third version with updated dates for T2P activities and minor corrections since v0.2 (ref. T2.PM.T2P.SOR) and editorial updates*.* |
| **1.0** | 06.09.2022 | ECB | MTRSG | Final version for distribution to T2 Participants |
| **1.1** | 14.11.2022 | ECB | MTRSG | Version including new dates following the postponement of the go-live date to 20 March 2023 and update on the Pre-Migration Day (section 8).  Version reviewed and approved by the TSWG. |

Table of Contents

[1 Introduction 4](#_Toc121933501)

[2 Pre-requisites 4](#_Toc121933502)

[3 Conditions 4](#_Toc121933503)

[4 Timings 4](#_Toc121933504)

[5 Reporting 5](#_Toc121933505)

[6 Co-management 5](#_Toc121933506)

[7 Pre-Migration activities 5](#_Toc121933507)

[7.1 Business process model and notation 5](#_Toc121933508)

[7.2 Activity tables 6](#_Toc121933509)

[8 Pre-Migration Day 19](#_Toc121933510)

[8.1 Business Day Schedule 19](#_Toc121933511)

[8.2 Reference data validation 20](#_Toc121933512)

[8.2.1 Verify Production data versus UTEST data 20](#_Toc121933513)

[8.2.2 Test the DN in CRDM 20](#_Toc121933514)

[8.2.3 Verify data extracts from CLM/RTGS 21](#_Toc121933515)

[8.2.4 RTGS Directory 21](#_Toc121933516)

[9 Reference documents 22](#_Toc121933517)

# Introduction

The Pre-Migration Schedule for T2 Participants (T2P) provides an overview of the Pre-Migration stage, the pre-requisites, conditions, timings, and the detailed description of activities. Each of these activities are described through a set of pre-defined categories to help the user understand the various aspects related to the activity. This document is also complemented by a Business Process Model Notation (BPMN) diagram which provides a high-level view of activities (green indicates optional).. . Following the postponement of the Go-Live date, an additional section has been added to describe the means to validate the production reference data before the go-live. This is covered in section 8 Pre-Migration Day.

# Pre-requisites

Prior to the start of the Pre-Migration stage, T2Ps must have fulfilled the following:

* Participants connectivity to ESMIG in Production has been established and verified. T2Ps are recommended to not only test the connectivity to ESMIG but also the connectivity to the underlying services CRDM, CLM, RTGS. This can be verified by using the Probe pages for U2A (for more details please refer to the [Connectivity guideline](https://www.ecb.europa.eu/paym/target/consolidation/profuse/html/index.en.html)s).
* Participants have submitted their registration forms to their Central Bank. The registration form template has been distributed by Central Banks to their communities. Supporting documentation on how to complete the form is available in the [TARGET Registration and On-boarding Guide.](file:///C:/Users/mariage/AppData/Roaming/OpenText/OTEdit/EC_darwin/c1689981213/C__Users_mariage_AppData_Roaming_OpenText_OTEdit_EC_darwin_c1689981213_T2%20Participants%20are%20advised%20to%20complete%20their%20Pre-Migration%20activities%20within%20the%20defined%20duration%20below._)

# Conditions

The Pre-Migration stage in Production is characterized by an organised approach split into the following four phases:

* T2 Operator reference data capture for Central Banks
* Central Banks system access and reference data capture configuration for their own party
* Central Banks reference data capture for their participants
* T2 Participants system access and reference data configuration for their own party

As opposed to the community-based approach, which was applied for Pre-migration in UTEST in order to advance and optimise the start of the UT stage a community level, the organised approach has set dates defined for the planned start and completion of the four phases. These harmonised dates were defined at Eurosystem level with the purpose to organise and monitor the progress of all participating communities within scheduled durations. These durations are based on the experiences from Central Bank Testing and User Testing.

# Timings

T2Ps can begin their system access and reference data configuration once their Central Bank has captured the necessary data for their party and created the required admin users (based on the provided Registration Form). Each Central Bank will communicate the planned start date for the T2P activities if different from the common Eurosystem start date 14 September. Some Central Banks may plan additional subsequent batches of party creations at their discretion. This may be due to the size of their community or select participants readiness. It is the responsibility of the Central Banks with additional batches to ensure that sufficient time is available for the participants to complete their configuration (e.g. create users, configure party and accounts) by **31 January 2023**. This date marks the end of the Pre-Migration stage.

# Reporting

T2Ps have to report to their Central Bank on the timely completion of their activities (format and frequency of reporting decided at CB level)

# Co-management

Co-managers are responsible for the timely and accurate configuration of their co-managees. A comprehensive guide on co-management requirements, responsibilities including examples are available in the Explainer on Co-Management (ref. link section 8)

# Pre-Migration activities

## Business process model and notation

The diagram below presents the sequence of activities to be carried out during the Pre-Migration stage. The activities are further detail in section 5.2.




Figure 1 - Business Process Model and Notation for T2P activities

## Activity tables

|  |  |
| --- | --- |
| **ID** | **T2.PM.T2P.SA** |
| **Activity Name** | System access |
| **Activity Group** | System access and registration data form verification (T2 participants) |
| **Actor** | T2 participant admin |
| **Data configuration (A2A, U2A)** | U2A – reaching the landing page and the T2 common components. |
| **Description** | In this activity the T2 participant admin will access CRDM, CLM and RTGS via the ESMIG portal. |
|  |  |
| **Prerequisites** | T2.PM.CB.PTY.ARC.CU  The T2 participant has provided the registration form(s) with the required data.  Hardware and software complies with the requirements as listed in the CRDM UHB section 1.2.1 Setup and login procedures |
| **Next activity**  **(i.e. activities for which this is a prerequisite)** | T2.PM.T2P.ARC.CU |
| **Optional** | No (Exemptions can apply e.g for co-managees) |
| **Reference UDFS** | N/A |
| **Reference UHB** | CRDM: 1.2.1 Setup and login procedures  CRDM: 1.2.5 User Administration |
| **Reconciliation means** | U2A: T2 participant admins are directed to an initial page named ESMIG portal that ensures proper routing to the web applications the user has been granted to enter. Once the user has accessed CRDM, the GUI should show the expected menu screens, fields, properties and functions, buttons and icons. |
| **Related privileges** | T2 participant admin privileges (configured by the CB as requested in the registration form provided by the T2 participant to the CB) |
| **Required role** | AH ESMIG Access |

|  |  |
| --- | --- |
| **ID** | **T2.PM.T2P.ARC.CU** |
| **Activity Name** | Access Rights Configuration |
| **Activity Group** | System access and registration data form verification (T2 participants) |
| **Actor** | T2 participant admin |
| **Data configuration (U2A)** | U2A:  Common 🡪 Access Rights Management 🡪 Users 🡪 New  Common 🡪 Access Rights Management 🡪 Grant/revoke roles 🡪 New/edit  Common 🡪 Access Rights Management 🡪 Certificate Distinguished Names 🡪 New |
| **Description** | The T2 participant admin will configure the access rights at user level, in order to assign the appropriate roles to all users of given party with the following tasks:   * Create and maintain user * Grant (and revoke) the (default and additional) roles * Create certificate DN * Create user certificate DN link |
| **Prerequisites** | T2.PM.T2P.SA |
| **Next activity**  **(i.e. activities for which this is a prerequisite)** | T2.PM.T2P.RFDV |
| **Optional** | No (Access rights configuration is required for all with own access. Exemptions can apply e.g for co-managees) |
| **Reference UDFS** | CRDM 1.2.2.1.4 User  CRDM 1.2.2.3.2 Configuration of access rights at user level |
| **Reference UHB** | CRDM UHB v2.0  2.3.3 Access Rights 2.3.3.3 User – New/Edit Screen 2.3.3.5 Certificate Distinguished Name – New Screen 2.3.3.5 Certificate Distinguished Name Links – New Screen  2.3.3.15 Grant/Revoke Role – New/Edit Screen |
| **Reconciliation means** | The participant Admin can go to Common 🡪 Access Rights Management 🡪 Users and check the search/list screen to verify the user was created. Click on the users details to verify the role assigned to the user. |
| **Related privileges** | Create Certificate Distinguish Name  Create User  Create User Certificate Distinguish Name Link  User Certificate DN Link Query  Access Rights Query  Update User  Privilege Query |
| **Required role** | AH ESMIG Access  AH Access Rights Admin  Party Administrator |

|  |  |
| --- | --- |
| **ID** | **T2.PM.T2P.RFDV** |
| **Activity Name** | Registration form data verification |
| **Activity Group** | System access and registration data form verification (T2 participants) |
| **Actor** | T2 participant user |
| **Data configuration (A2A, U2A)** | U2A: |
| **Description** | The T2 participant user will verify that the data visible in the system matches the data input from the registration form(s). This includes   * Main information, general information on the Party; * Technical addresses, to define the Distinguished Names (DNs) that are authorized by the Party for the different services; * Service Link/s, to determine the participation type in the different services; * Information dedicated to specific TARGET services, that is defined at the Party level; * Invoice configuration, for completing the information needed for the billing set-up; |
| **Prerequisites** | The T2 participant admin has completed system access and created the users who will verify the registration form data in the system.  T2.PM.T2P.ARC.CU |
| **Next activity**  **(i.e. activities for which this is a prerequisite)** | T2.PM.T2P.RC |
| **Optional** | Yes (exemptions apply for co-managees) |
| **Reference UDFS** | N/A |
| **Reference UHB** | N/A |
| **Reconciliation means** | The T2 participant admin user can verify and confirm that all data provided in the registration form is present in the system. |
| **Related privileges** | Relevant query privileges (depends on the Reference Data that needs to be verified), e.g:  System Entity Query  Party Reference Data Query  Party-Service Link List Query  Cash Account List Query  Authorised Account User Query |
| **Required role** | AH ESMIG Access  AH CRDM Reader |

|  |  |
| --- | --- |
| **ID** | **T2.PM.T2P.RC** |
| **Activity Name** | Routing configuration |
| **Activity Group** | Party configuration (T2 participant) |
| **Actor** | T2 participant user |
| **Data configuration (U2A)** | U2A:  Common 🡪 Network Configuration 🡪 Routing 🡪New  Common 🡪 Network Configuration 🡪 DN-BIC Routing 🡪New |
| **Description** | Routing configurations specify the technical elements that are used to send a given outgoing message to the relevant actor. The routing configuration allows the setting up of either a default routing which is used when no specific conditions are defined for a party and a specific outgoing message or dedicated routings for specific outgoing messages. This configuration has to be done for every network service e.g. message store and forward etc. Routing Configuration has to be active, if T2Ps wish to receive the RTGS directory on 08th of February.  Each T2 participant is responsible for maintaining the reference data for their DN-BIC routing links (only applicable to RTGS message flows). For Inbound communication, different DNs can be linked to different BICs and vice versa. In the outbound case, the same BIC can only be linked to a single DN. However different BICs can still be linked to the same DN.  If set to Outbound, a DN can only be linked to no more than one BIC. |
| **Prerequisites** | T2.PM.T2P.ARC.CU |
| **Next activity**  **(i.e. activities for which this is a prerequisite)** | T2.PM.T2P.MSG.RC |
| **Optional** | No, except for U2A only users and co-managee parties that meet the requirements of CSLD-0113-SYS |
| **Reference UDFS** | CRDM UDFS v2.2  1.2.1 Connectivity |
| **Reference UHB** | CRDM  2.3.6.4 Routing  2.3.6.1 Distinguished Name – BIC Routing – Search/List Screen  2.3.6.2 Distinguished Name – BIC Routing – New/Edit Screen) 3.4.1.5 Create a Distinguished Name-BIC routing configuration |
| **Reconciliation means** | U2A: Users can go to  Common 🡪 Network Configuration 🡪 Routing 🡪 Search and enter any known search criteria to view the list of routing between party and services.  Common 🡪 Network Configuration 🡪 DN-BIC Routing 🡪 enter search criteria to display a list of DN-BIC couples matching the entered search criteria. |
| **Related privileges** | Create Routing  Create DN-BIC routing,  Routing list query  Update Routing  Update DN-BIC routing,  DN BIC Routing query. |
| **Required role** | AH ESMIG Access  AH CRDM Configuration Manager  AH Access Rights Admin  AH CRDM Reader |

|  |  |
| --- | --- |
| **ID** | **T2.PM.T2P.MSG.RC** |
| **Activity Name** | Report Configuration |
| **Activity Group** | Party Configuration (T2 participant) |
| **Actor** | T2 participant user |
| **Data configuration (U2A)** | U2A: Common 🡪 Messages and Reports 🡪 Report Configuration 🡪 New |
| **Description:** | The T2 participant user will configure the reports that the T2 participant wants to receive  Note: users who wish to receive the RTGS directory on 8 February must set the valid from date of their Report configuration to 08.02.2023 (or earlier) |
| **Prerequisites** | T2.PM.T2P.RC |
| **Next activity**  **(i.e. activities for which this is a prerequisite)** | T2.PM.T2P.MSG.RSC |
| **Optional** | Yes |
| **Reference UDFS** | CRDM  1.3.7. Report configuration  CLM  3.2.4 Messaging (Report configuration)  5.7.2 CLM report generation (Statement of Accounts)  RTGS  3.2.4 Messaging (Report configuration)  5.6.2 RTGS report generation (required RTGS Directory and Statement of Accounts) |
| **Reference UHB** | CRDM UHB v2.0  3.6.1 Report Management  3.6.1.1 Create a New Report Configuration |
| **Reconciliation means** | U2A: Users can go to Common 🡪 Messages and Reports 🡪 Report Configurations 🡪 Search and enter any known search criteria to view the list of report configuration. Select the relevant row and check the details to verify the data input was correctly captured. (CRDM UHB 3.5 Reports) |
| **Related privileges** | Report configuration list query  Report configuration details query  Create report configuration  Update report configuration |
| **Required role** | AH ESMIG Access  AH CRDM Configuration Manager  AH CRDM Reader |

|  |  |
| --- | --- |
| **ID** | **T2.PM.T2P.MSG.RSC** |
| **Activity Name** | Message subscription rule set configuration |
| **Activity Group** | Party configuration (T2 participant) |
| **Actor** | T2 participant user |
| **Data configuration (A2A, U2A)** | Common 🡪 Messages and Reports 🡪 Message Subscription Rule Set 🡪 New |
| **Description:** | The T2 participant user can configure the specific set of messages it wants to receive from individual services and components for T2 participants and accounts.  Each message subscription rule set is defined by the following elements:   * the name and the description of the message subscription rule set; (e.g. for camt.054, pacs.002, camt.077) * the service to which the Message Subscription Rule Set shall be applied for. * a validity period, specified by a mandatory initial date of validity and an optional final date of validity; * a set of subscribing interested parties to which the relevant service or component sends all the messages matching the rule set; |
| **Prerequisites** | T2.PM.T2P.MSG.RC |
| **Next activity**  **(i.e. activities for which this is a prerequisite)** | T2.PM.T2P.MSG.MSC |
| **Optional** | No, except for U2A only users and co-managee parties that meet the requirements of CSLD-0113-SYS) |
| **Reference UDFS** | CRDM UDFS v2.2  1.3.5 – Message subscription configuration |
| **Reference UHB** | CRDM UHB v2.0  2.3.4.1 Message Subscription Rule Sets – Search/List Screen  2.3.4.2 Message Subscription Rule Set – Details Screen Context of Usage |
| **Reconciliation means** | U2A: Users can go to Common🡪 Messages and Reports 🡪 MSRS 🡪 Search and enter any known search criteria to view the list of message subscription rule sets. Select the relevant row and check the details to verify the data input was correctly submitted. |
| **Related privileges** | Create Message Subscription Rule Set  Message subscription rule set details query  Delete message subscription rule set  Message subscription rule list query  Update message subscription rule  Delete message subscription rule |
| **Required role** | AH ESMIG Access  AH CRDM Configuration Manager  AH CRDM Reader |

|  |  |
| --- | --- |
| **ID** | **T2.PM.T2P.MSG.MSC** |
| **Activity Name** | Message subscription rules |
| **Activity Group** | Party configuration (T2 participant) |
| **Actor** | T2 participant user |
| **Data configuration (U2A)** | U2A: Common🡪 Messages and Reports 🡪 MSRS 🡪 Search 🡪 Details 🡪 New Message Rule |
| **Description:** | The T2 participant user will set up message subscription rules, to be connected to an existing message subscription rule set.for the T2P’s parties and accounts. |
| **Prerequisites** | T2.PM.T2P.MSG.RSC |
| **Next activity**  **(i.e. activities for which this is a prerequisite)** | N/A |
| **Optional** | No (except for U2A only) |
| **Reference UDFS** | CRDM UDFS v2.2  1.2.3 Message subscription  4.5.3.8 Message Subscription Rule - New |
| **Reference UHB** | CRDM UHB v2.0  2.3.4.1 Message Subscription Rule Sets – Search/List Screen  2.3.4.4 Message Subscription Rule – New/Edit Screen  4.1.15 Message Subscription Rule |
| **Reconciliation means** | U2A: User can go to Common🡪 Messages and Reports 🡪 Message Subscription Rules Set 🡪 Search and enter any know search criteria to view the list of rule sets. Select the rules set to which the rule was added, then click on details to verify that the rule was correctly captured in the rules set. |
| **Related privileges** | Message subscription rule set list query  Message subscription rule set details query  Message subscription rule list query  Update Message Subscription Rule Set and Message Subscription Rule Set List Query |
| **Required role** | AH ESMIG Access  AH CRDM Configuration Manager  AH CRDM Reader |

|  |  |
| --- | --- |
| **ID** | **T2.PM.T2P.DCA.AC** |
| **Activity Name** | CLM and RTGS accounts configuration |
| **Activity Group** | Party configuration (T2 participant) |
| **Actor** | T2 participant user |
| **Data configuration (A2A, U2A)** | U2A:  COMMON 🡪 Cash 🡪 Limits 🡪 New  COMMON 🡪 Cash 🡪 Cash Accounts 🡪 Search 🡪 click on New or Edit button  (to configure the Account Threshold)  A2A:  ModifyLimit (camt.011) |
| **Description** | The T2 participant user will configure:  Limit  Standing Order for Limit (bilateral/multilateral)  Liquidity Transfer Order  Account Threshold Configuration:  Payment Bank users can only edit floor/ceiling attributes for Cash Accounts under their datascope and for the ones for which they have been defined as Co-Manager.  Please note.   * Minimum amount for a standing order for limit is EUR 1,000,000 * Setting to “0“ of the amount of a standing order for limit has a similar effect as the deletion of a standing order for limit. |
| **Prerequisites** | T2.PM.CB.PTY.RFDV |
| **Next activity**  **(i.e. activities for which this is a prerequisite)** | T2.PM.T2P.DCA.SOR |
| **Optional** | Yes |
| **Reference UDFS** | CRDM UDFS v2.2  1.3.3.3. Description of the entities/1.Cash account  1.3.3.3. Description of the entities/2. Limit  1.3.3.3. Description of the entities/3. Standing order for Limit  1.3.3.3. Description of the entities/5. Liquidity Transfer Order  1.3.3.3. Description of the entities/7. Account Threshold Configuration  3.1.1.7. ModifyLimit (camt.011) |
| **Reference UHB** | CRDM UHB v2.0  2.3.2.3 Cash Account  2.3.2.5 Limit |
|  |  |
| **Reconciliation means** | U2A:  Users can go to COMMON 🡪 Cash 🡪 Standing/Predefined Liquidity Transfer Order 🡪 Search and enter any known search criteria to view the list of standing liquidity transfer orders.  User can go to COMMON 🡪 Cash 🡪 Limits 🡪 Search and enter any known search criteria to view the list of configured limits related to the cash accounts.  A2A:  Users will receive a Receipt(camt.025) in return from the camt.024 message.  Users will receive a Receipt(camt.025) in return from the camt.011 message. |
| **Related privileges** | Create Liquidity Transfer Order  Update Liquidity Transfer Order  Create Limit  Update Limit  Cash Account list query  Cash Account reference data query  DCA\_UpdateT2SDedicatedCashAccount |
| **Required role** | AH ESMIG Access  AH CRDM Liquidity Manager  AH CRDM Reader |

|  |  |
| --- | --- |
| **ID** | **T2.PM.T2P.SOR** |
| **Activity Name** | Standing Order (T2 participants CLM and RTGS accounts) |
| **Activity Group** | Party configuration (T2 participant) |
| **Actor** | T2 participant user |
| **Data configuration (A2A, U2A)** | U2A: COMMON 🡪 Cash 🡪 Standing Order for Reservation🡪 New  U2A: COMMON 🡪 Cash 🡪 Standing/Predefined Liquidity Transfer Order 🡪 New  A2A: ModifyStandingOrder (camt.024) |
| **Description** | Creation of a new Standing Order for a T2 participants CLM and RTGS accounts, specifying the priority, amount, cash account number, and Valid To and From.  User can create standing orders with the following type:   * Predefined * Standing * Rule-based floor * Rule-based ceiling   Note:  T2Ps must close their current T2S Standing Orders to TARGET2 as of business day 20/03.  After the migration to T2, T2Ps who wish to have the liquidity sent back to its MCA should set up new standing orders in CRDM as the automatic cash sweep will cease to exist. This is however optional as the balance can remain on a T2S DCA overnight. It will still be calculated in the automatic marginal lending and considered for the minimum reserve. A Liquidity Transfer to Overnight Deposit is only possible from the MCA.  The creation of standing orders should be completed by 31 of January as part of the Pre-Migration activities, however, these can be modified during the Pre-Migration Day period up until 10 March. |
| **Prerequisites** | T2.PM.CB.PTY.DCA.AC |
| **Next activity**  **(i.e. activities for which this is a prerequisite)** | T2.PM.T2P.AMGC |
| **Optional** | Yes |
| **Reference UDFS** | RTGS UDFS v2.2  3.1 Parties and Accounts)  3.2 Accounts structure and functionalities  3.2.3 Functionalities  CRDM UDFS v2.2  1.3.3.3. Description of the entities/1.Cash Account  3.1.1.1. ModifyStandingOrder (camt.024) |
| **Reference UHB** | CRDM UHB v2.0  2.4.1.13 Standing Order for Reservation – New/Edit Screen  2.3.2.8 Standing/Predefined Liquidity Transfer Order – Search/List Screen  2.3.2.9 Standing/Predefined Liquidity Transfer Order – Details Screen  2.3.2.10 Standing/Predefined Liquidity Transfer Order – New/Edit Screen |
| **Reconciliation means** | U2A: Users can go to T2 🡪 Cash 🡪 Standing Orders for Reservation 🡪 Search and enter any known search criteria to view the list of standing orders for reservation. A2A: Users will receive a Receipt(camt.025) in return from the camt.024 message. |
| **Related privileges** | Create Standing Order for Reservation  Standing Order for Reservation List Query  Standing Order for Reservation Details Query  Update Standing Order for Reservation |
| **Required role** | AH ESMIG Access  AH CRDM Liquidity Manager  AH CRDM Reader |

|  |  |
| --- | --- |
| **ID** | **T2.PM.T2P.AMGC** |
| **Activity Name** | Account Monitoring Group Configuration |
| **Activity Group** | Party configuration (T2 participant) |
| **Actor** | T2 participant user |
| **Data configuration (U2A)** | U2A: T2 🡪 Cash 🡪 Account Monitoring Group 🡪 New |
| **Description** | An Account Monitoring Group is an optional group of accounts (MCA(s) and DCA(s)). It grants a collective view over the liquidity of the involved accounts to payment banks. An Account Monitoring Group is used for liquidity monitoring purposes of payment banks; they are not used for the context of payment orders or liquidity transfer orders settlement. The leader party of the Account Monitoring Group can see the liquidity of all included accounts while the other participants of the Account Monitoring Group can only see the liquidity of their accounts.  Payment banks can set up an Account Monitoring Group and specify the name of this group. The Account Holder, which sets up the Account Monitoring Group, is defined as leader party of the Account Monitoring Group. Each payment bank can then optionally add MCAs in his data scope to the Account Monitoring Group. All actions (set up, modify, delete) become effective as of the next business day or on the activation date. |
| **Prerequisites: Internal activities** | T2.PM.CB.PTY.MCA.CLM  T2.PM.CB.PTY.DCA.RTGS |
| **Next activity**  **(i.e. activities for which this is a prerequisite)** | None |
| **Optional** | Yes |
| **Reference UDFS** | CRDM UDFS v2.2  1.2.4. Graphical user interface  CLM UDFS  3.4 Type of group |
| **Reference UHB** | CRDM UHB v2.0  2.4.1.3 - Account Monitoring Group |
| **Reconciliation means** | U2A: Users can go to T2 🡪 Cash 🡪 Account Monitoring Group 🡪 Search and enter any known search criteria to view the list of Account monitoring group names To view the details, select the row with the group name that was created, click on Details on the right side of the search list and verify that the data submitted corresponds to the list of details. |
| **Related privileges** | Create Account Monitoring Group  Account Monitoring Group query  Update Account Monitoring Group  Account Monitoring Group Details Query |
| **Required role** | AH ESMIG Access  AH CRDM Configuration Manager  AH CRDM Reader  AH CRDM AMG Manager |

# Pre-Migration Day

After the Pre-Migration stage, the CBs and T2Ps will begin the *Pre-Migration Day* period from 8 February 20223 until 10 March 2023. Although the Pre-Migration Day stretches over a longer period of time, it remains in the same BD of 17 March. The objective of this phase is for CBs and T2Ps to validate the data which is propagated (copied) from CRDM to intermediary CLM/RTGS tables. In addition, it is recommended that users verify that the reference data captured during the Pre-Migration in CRDM is correct, consistent and complete. To ensure this, pre-check data propagations from CRDM to CLM/RTGS will be processed on a weekly basis starting Wednesday 8 February 2023. Any inconsistencies detected will be reported by the T2 Operator to the Central Banks who will either correct the data or request the participants to correct it depending on the nature of the error reported. Once the data is corrected, the following pre-check data propagation will confirm that the correction was successfully completed.

For more information on the CRDM configuration, please refer to the available documents i.e UDFS, Clarification note on CLM/RTGS reference data, and *CRDM Configuration Guidelines for Payment Banks and Ancillary Systems relevant in CLM/RTGS.*

## Business Day Schedule

A reduced business day schedule is foreseen for the Pre-Migration Day and a dedicated chain of processes has to run before the start of the first business day on the Migration Weekend.

These processes include:

* (pre-check) data propagation processes in CRDM
* data loading processes in CLM and RTGS
* activation of reference data

The above-mentioned processes will be triggered by a dedicated pre-migration schedule for data loading which is coordinated by the common component Business Day Management (BDM).

The following events are foreseen on the **pre-migration business day.** On the pre-migration day no payment order processing can take place:

|  |  |  |
| --- | --- | --- |
| **Code** | **Event** | **A2A interaction** |
| CT01 | Load CLM business day | No A2A payment business |
| STOP | STOP Event |  |
| T2RD (can be scheduled more than once) | Create RTGS Directory and CLM Repository (in CRDM, but part of the T2 schedule) | No A2A payment business |
| STOP | STOP Event |  |
| T2DC (can be scheduled more than once per business day) | Test data propagation by CRDM – for Pre-Check | No A2A payment business |
| STOP | STOP Event |  |
| T2PC (can be scheduled more than once per business day) | Pre-check of test data propagation in CLM/RTGS | No A2A payment business |
| STOP | STOP Event |  |

As data propagation processes are linked to CLM events only, no RTGS events are needed.

## Reference data validation

In order to validate the reference data captured during Pre-Migration, CBs and T2Ps should follow to instructions below:

### Verify Production data versus UTEST data

All CBs and T2Ps have verified their CRDM configurations versus their CRDM configuration in UTEST. T2Ps should pay particular attention to the configuration related to their users;

* + DNs may be different in PROD and UTEST 🡪 check with your IT
  + All DNs are correct 🡪 no typing errors
  + All DNs (PTA, A2A, U2A) are in correct format
  + All users are linked to its DN
  + Relevant Roles are granted to all U2A/A2A users

For more information on the format of DNs, please refer to the Clarification Note [CRDM Configuration Guidelines for Payment Banks and Ancillary Systems relevant in CLM/RTGS](https://www.dnb.nl/media/q44fotl2/t2-crdm-configuration-guide-for-payment-banks_1-0.docx)

It should be noted that CBs are only able to verify the generic format of the DNs but cannot validate the business content (e.g typos, wrong spacing).

### Test the DN in CRDM

T2Ps should perform a first test to check the set-up of their DN is in line with the data used / provided by ESMIG. For this, the T2 Actor can send an A2A query to CRDM already during the Pre-Migration stage and Pre-Migration day. Details on the A2A queries available in CRDM are available in the CRDM UDFS[[1]](#footnote-1).

One query which might be used is the AccountQueryList (see chapter 3.1.2.1). The message should be composed by the Business Application Header (BAH) and the acmt.025 message payload. The DN who signed the message and the System User contained in the BAH should be properly configured in CRDM.

In case the configuration is correctly performed, an **acmt.026** is sent as answer, containing the requested information or an **IIMP0XX** Business Rule (e.g. IIMP054, IIMP055, IIMP056).

### Verify data extracts from CLM/RTGS

Co-managers and CMPs should verify the extracts of data configurations from the weekly pre-check data propagations to CLM/RTGS versus the CRDM reference data in Production. The data extracts will be provided by the CB. In case of co-management, the CB of the co-managee will provide the extracts.

### RTGS Directory

The RTGS Directorygeneration is part of “Pre-migration day” process and is generated with the specific event T2RD a weekly basis until Wednesday 8 March 2023 (ref. section 8.1). This event will also trigger the creation and distribution of the CLM Repository. The creation and distribution of RTGS Directory and CLM Repository is only triggered if an open and valid report configuration has been set-up in CRDM. For this, the report configuration must have a *Valid from date* of its subscription of 2023-02-08 (or an earlier date).

Only full versions are generated and sent during “Pre-migration day”, regardless of the ordering method (delta or full mode). Also, all further reports created on the same business date (i.e. when the event will be triggered more than once during the pre-migration day) will be created as a “full” version. If an RTGS Directory Update and/or CLM Repository Update report configuration has been set-up with a Valid From date prior to the go-live date, then the first “delta” version of the file would be created and distributed on the go-live (i.e. business date Monday 20 March 2023). After Go-live, RTGS Directory generation is part of the normal T2 EOD/SOD processing.

The RTGS Directory is generated taking the current business date (i.e. the pre-migration day date) as reference and extracting the data from the Authorised Account User and BIC Directory data defined in CRDM. In a scenario where the Authorised Account User data is set up with validity periods starting from the go-live date, the RTGS Directory generated on the pre-migration day date will take into account inclusion records but not exclusion records. Specifically, for a given business date,

* all future Authorised Account User records apart from exclusions (i.e. records with a “Valid From” later than the pre-migration day date) will be included,
* exclusion records will only be taken into account if valid on the date of the extraction.

It is also possible to create Authorised Account User data for exclusions with a valid from date prior to the opening date of the Cash Account. Therefore, in order to have the correct excluded records from the first generation of the RTGS Directory, AAU with Participation Type “Exclusion” (and only those) may be created with valid from date equal to the pre-migration day date.

Note: The valid from date of already created data (i.e. based on the previous assumption for the go-live date) does not need to be changed.

# Reference documents

* [T2 Migration, Testing and Readiness Strategy](https://www.ecb.europa.eu/paym/pdf/consultations/T2_Migration_Testing_and_Readiness_Strategy_2.0.pdf)
* [CRDM User Detailed Functional Specifications](https://www.ecb.europa.eu/paym/target/consolidation/profuse/shared/pdf/2021-04-01_t2_udfs_crdm_v2-2.pdf)
* [CRDM User Handbook](https://www.ecb.europa.eu/paym/target/consolidation/profuse/shared/pdf/2021-05-19_crdm_uhb_v2-0.pdf)
* [Explainer on CRDM terms and concepts for T2](https://www.ecb.europa.eu/paym/target/consolidation/profuse/shared/pdf/ExplaineronCRDMTerms.en.pdf)
* [Explainer on Co-Management](https://www.ecb.europa.eu/paym/target/consolidation/profuse/shared/pdf/explainer_on_co-management.pdf)
* [CRDM Configuration Guidelines for Payment Banks and Ancillary Systems relevant in CLM/RTGS (distributed by Central Banks)](https://www.ecb.europa.eu/paym/target/consolidation/profuse/shared/pdf/T2CRDMConfigurationGuideforPaymentBanks.en.pdf)

Additional reference documents are available on the [ECB website for professional use](https://www.ecb.europa.eu/paym/target/consolidation/profuse/html/index.en.html)

1. https://www.ecb.europa.eu/paym/target/consolidation/profuse/shared/pdf/2021-04-01\_t2\_udfs\_crdm\_v2-2.pdf [↑](#footnote-ref-1)